## Sheet1
Section | Details
Objective | Ensure Number to Words API functions correctly
Scope | Functional Testing
Scope | Performance Testing
Scope | Security Testing
Scope | Manual and Automated Testing
Scope | Test API in different environments
Inclusions | Functional testing, Schema validation, Performance testing, Security testing
Exclusions | UI-based testing, Non-related endpoints
Test Environments | Windows, macOS, Linux
Test Environments | Postman, SOAP UI, JMeter, OWASP ZAP
Test Environments | API authentication checks
Test Environments | Ensure encrypted connections (HTTPS)
Defect Reporting Procedure | API returns incorrect number-to-word conversion
Defect Reporting Procedure | Improper XML response formatting
Defect Reporting Procedure | API does not handle negative/zero values correctly
Defect Reporting Procedure | API response is slow (>2s for simple requests)
Defect Reporting Procedure | Security vulnerabilities detected
Test Strategy | Test Case Creation using Equivalence Partitioning, Boundary Value Analysis
Test Strategy | Smoke Testing
Test Strategy | Regression Testing
Test Strategy | Security Testing
Test Schedule | Test Plan Creation - 2 Days, Test Execution - 5 Days, Security Testing - 3 Days
Test Deliverables | Entry and Exit Criteria for Test Execution and Closure
Entry and Exit Criteria | Entry: API available for testing, Exit: Defects logged and resolved
Entry and Exit Criteria | Test summary report prepared
Tools Used | JIRA, Postman, JMeter, OWASP ZAP, Confluence
Risks and Mitigations | Risk: API Downtime - Mitigation: Backup test environment
Approvals | Signatures from QA Lead, Project Manager, Client Representative